| Week | P1 (ML) | P4 (Hybrid) | P2 (Cyber) | P3 (Fullstack) |
| --- | --- | --- | --- | --- |
| 1–2 | Data pipeline, dataset curation | Literature/attack-code prep (FGSM/PGD) | — | — |
| 3–4 | Train RF/NN/Autoencoder; cross-dataset eval | Prep continues; design BCL signal schema | Literature/federated-learning prep | — |
| 5 | Finalize baseline artifacts + write Paper 1 | Begin full BCL build using near-final P1 models | — | — |
| 6–7 | (Paper 1 in review/write-up) | Attack baseline, build BCL, adaptive-attacker tests | Design secure aggregation protocol | Literature/XAI-tooling prep |
| 8–9 | — | Finalize BCL system + write Paper 2 | Begin federating P4's near-final BCL model | — |
| 9–10 | — | (Paper 2 in review/write-up) | Secure aggregation, privacy-robustness ablation | Design SHAP/LIME integration + dashboard architecture |
| 12–13 | — | — | Finalize federated system + write Paper 3 | Begin SHAP integration using near-final P2 model |
| 13–15 | — | — | (Paper 3 in review/write-up) | Build SHAP-drift signal, integrate dashboard, run full-stack demo |
| 16–17 | — | — | — | Finalize integration + write Paper 4 |
| 17–18 | All four: cross-reference papers, joint related-work pass, plagiarism/AI-detection checks, submit as a coordinated series |  |  |  |